## Master NPI Status
| Programme committed | Beta | GA |  | FBP Rls | Succession CSE1000 Compatible | Sales Presentation / Product Overview | Pricing (Indicative) | Product Positioning (Nortel & Competitor) | Channel Impact Guidelines | Type Approval | MIC / Product Bulletin | Technical Training | Pricing (Final) | Sales Training | Collateral/Sales Tools
Primes: |  | Nortel | Nortel | Status |  | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel | Nortel
[6 empty] | NPI | ProdMktg | ProdMktg | ProdMktg | NPI | NPI | NPI | NPI | Pricing | ProdMktg | ProdMktg
Meridian 1
Products GA in 1999-Q2 2001 | Note: Products in shaded cells may may have a non current status, Please check with your respective Nortel Product contact
X.11 Release 25.15 | 3 | 2000-01-01 | 2000-05-01 | passed | 2.2.1 | N/A | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 |  | 3
MAT Rls 6.6 | 3 | 2000-01-01 | 2000-05-01 | passed | 2.2.1 | N/A | 3 | 3 | 3 |  | N/A | 3 | 3 | 3 |  | 3
MAT Rls 6.6 (German/French) | 3 | 2000-10-01 | 2000-12-08 | passed | 2.2.1 | N/A | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 |  | 3
Meridian HomeOffice II | 3 | 1998-12-01 | 1999-02-02 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | 3 | 3
MIRAN II | 3 | 1999-05-01 | 1999-09-02 | passed | 1.2 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | N/R | 3
MICB II | 3 | 1999-05-01 | 1999-09-09 | passed | 1.2 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | N/R | 3
ITG Rls 1 | 3 | 1999-05-01 | 1999-08-16 | passed | 1.2 |  | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 |  | 3
BRAVO I | 3 | 1999-08-01 | 1999-10-22 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | 3 | 3
X.11 Release 24B | 3 | 1999-04-01 | 1999-08-28 | passed | 2.1 |  | 3 | 3 | N/A | N/A | N/A | 3 | 3 | 3 | 3 | 3
Option 11C Mini | 3 | 1999-05-01 | 1999-07-08 | passed | 2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | N/R | 3
Option 11C LSE Phase 1 | 3 | 1999-04-01 | 1999-06-12 | passed | 2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 |  | 3
MAT Rls 6.5 | 3 | 1999-04-01 | 1999-09-01 | passed | 1.2 |  | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | 3 | 3
Meridian Set M39xx Ph. 1 | 3 | 1999-04-01 | 1999-10-29 | passed | 2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | N/R | 3 | N/R | 3
Orion ATA (Analogue Terminal Adapter) | 3 | 1999-08-01 | 1999-10-04 | passed |  |  | 3 | 3 | 3 | N/A | 3 | 3 | N/R | 3 |  | N/R
CP4 (68060) | 3 | 1998-11-01 | 1999-08-28 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | N/R | 3 | N/R | N/R
i1010 IP Telecommuter | 3 | 1999-08-01 | 2000-01-01 | cntlrls | 2.2.1 |  | 3 | 3 | 3 |  | N/A | 3 | 3 | 3 |  | 3
M39xx Display Based Module | 3 | 2000-09-01 | 2000-12-01 | passed | 2.2.1 | Yes-Remote Office Required | 3 | 3 | 3 | N/A | 3 | 3 | N/A | 3 | 3 | 3
M39xx Key Based Expansion Module | 3 | 2000-09-01 | 2000-12-01 | passed | 2.3 | Yes-Remote Office Required | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | 3 | 3
Option 81C CP Pentium II | 3 | 2000-03-01 | 2000-10-01 | passed | 2.2.1 / 2.3 | N/A | 3 | 3 | 3 | 3 | N/R | 3 | 3 | 3 |  | N/A
Fibre Network Fabric (FNF) | 3 | 2000-02-01 | 2000-10-01 | passed | 2.2.1 / 2.3 | N/A | 3 | 3 | 3 | 3 | N/R | 3 | 3 | 3 |  | N/A
MDECT
MDECT C4040 Docking Station | 3 | 1999-05-01 | 1999-08-11 | passed |  |  | 3 | 3 | 3 | N/A | 3 | 3 | N/R | 3 | N/R | N/R
MDECT Windows Manager | 3 | 1999-02-01 | 1999-07-30 | passed |  |  | 3 | 3 |  | N/A | N/A | 3 | N/R | 3 | N/R | N/R
MDECT C4010 Handset | 3 | 1999-05-01 | 1999-07-25 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | N/R | 3 | N/R | 3
MDECT Capacity Enhancement | 3 | 1999-04-01 | 1999-10-08 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | N/A | 3 | N/R | 3 | N/R | N/R
MDECT CTI Phase 1 (Alarms Sever) | 3 | 1999-09-01 | 2000-04-07 | passed |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MDECT MWI | 3 | 1999-11-01 | 2000-01-01 | passed |  |  | 3 | 3 | 3 | N/A | N/A | 3 | N/A | 3 | 3 | 3
MDECT 4010Ex (Int safe h/set) | 3 | 1999-11-01 | 2000-03-01 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | N/A | 3 | 3 | 3
MDECT 4020 (handset) | 3 | 1999-11-01 | 2000-03-01 | passed | 2.2.1 |  | 3 | 3 | 3 | N/A | 3 | 3 | N/A | 3 | 3 | 3
MDECT 2000 (MSMN) | 3 | 2000-02-01 | 2000-05-04 | passed | 1.2 / 2.2.1 | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
Messaging
New Card Option Mail / M.Mail 12 | 3 | 1999-07-01 | 1999-09-01 | passed | 1.2 |  | 3 | 3 | 3 | 1 | N/A | 3 | N/A | 3 | N/A | N/A
Products GA in 1999-Q2 2001 | Use '+' to UnGroup and '-' to Group
Products GA for 2001/2002 |  | Beta | GA
Optivity Telephony Manager 1.0 | 3 | 2000-05-01 | 2000-08-30 | passed | 1.2 / 2.2.1 | N/A | 3 | 3 | 3 |  | N/A | 3 | 3 | 3 |  | 3
OTM 1.01 (German/French) & BugFix | 3 | 2000-11-01 | 2001-01-11 | passed | 2.3 | N/A | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 |  | 3
ITG Trunk Rls 2.0 | 3 | 2000-01-01 | 31/05/00 | passed | 1.2 / 2.2.1 | No | 3 | 3 | 3 | 2 | 3 | 2 | 3 | 3 | TBC | 2
Meridian 1 Core
Rls 25.40/B | 3 | 2001-04-17 | 0302/0802 | passed | 3.1 | N/A | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | N/A | N/A
Rls 26 | 2 | TBD | TBD |  | TBD | N/A
MIPCD | 3 | 2000-01-01 | 2001-03-22 | passed | 2.3 | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Miran III | 3 | 2001-12-01 | 2002-05-31 | passed | 3.1 | Yes | 3 | 3 | 3 | 1 | N/A | 3 | 3 | 3
MICB III | 3 | 2002-02-01 | 2002-07-08 | passed | 3.1 | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
DDP2 - PRI2/DTI pack replacement | 3 | 2001-12-01 | 2002-05-20 | passed | 3.1.1 | No | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | N/A | N/A
Terminals and Accessories
Ascom Smile2 | 2 | 2001-05-01 | 2002-04-01 | passed | N/A | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 1
Meridian Set M39xx Phase 3 | 3 | 2001-08-01 | 2002-05-25 | passed | 3.1 | Yes-Remote Office Required | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | N/A | 3
M39xx ATA (Analogue Terminal Adapter) | 3 | 2000-09-01 | 2002-08-23 | passed | 2.2.1 | Yes-Remote Office Required | 3 | 3 | 3 |  | 3 | 2 | N/A | 3 | N/A
CTIA (Rls 25.40 dependant) | 3 | Q1 2001 | 2002-05-25 | passed | 2.4 | Yes-Remote Office Required | 3 | 3 | 3 |  | 3 | 3 | N/A | 3 | N/A
Full Duplex Handsfree (FDHF) | 3 | 2001-08-01 | 2002-05-25 | passed | 3.1 | Yes-Remote Office Required | 3 | 3 | 3 | N/A | 3 | 2 | 3 | 3 | 2 | 2
i2004 IP Set | Included in Rls1.0 of Succession CSE 1000. For i2004 on Meridian, see IP Line 2.0 / 2.1, in the "IP Telephony on Meridian 1" section.
Internet Telephony Switch Module | 3 | 2001-03-01 | 2001-04-01 | passed | 2.3 | Yes | 3 | 3 | 3 |  | N/A | 3 | N/A | 3 | N/A | N/A
Power In-Line Patch Panel | 3 | June 2001 | 2001-10-01 | passed | 2.4 | Yes | 3 | 3 | 3 | N/A | N/A | 3 | N/A | 3 | N/A | N/A
802.1Q on i2004 |  | 2002-06-02 | Sept week 1 | passed | N/A | Yes | 3 | 3 | 3 |  | N/A | 2 | N/A | 3 | N/A | N/A
i2004 improvements - Phase I | 3 | 2002-08-01 | 2002-11-01 |  | TBD | Yes | 2 | 2 | 2 |  | N/A | 2 | N/A | 2 | N/A | N/A
i2004 improvements - Phase II | 2 | TBD | TBD |  | TBD | Yes |  |  |  |  | N/A |  | N/A |  | N/A | N/A
i2050 Softphone | Included in Rls1.1 of Succession CSE 1000. For i2004 on Meridian, see IP Line 2.2, in the "IP Telephony on Meridian 1" section.
i2002 on Succession CSE 1000 Rls 2 | 3 | 2002-06-01 | 29th October | passed | 4.0 | Yes | [6 empty] | N/A
i2002 on X11/M1 | 3 | Nov wk1 | TBD |  | 4.0 | NA
IP Telephony on Meridian 1
IP Line 2.1 and i2004 IP Set | 3 | 2000-03-01 | 2001-02-28 | passed | 2.2.1 / 2.3 | Yes | 3 | 3 | 3 |  | 3 | 3 | 3 |  | N/A
IP Line 2.2 and i2050 softphone | 3 | 2001-08-01 | 2002-03-25 | passed | 3.1 | Yes | 3 | 3 | 3 |  | 3 | 3 | N/A |  | N/A | N/A
IP Line 3.0 | 3 | 2002-06-17 | 2002-10-31 | passed | 4.0 | Yes
ITG Trunk 2.1 | 3 | 2001-10-01 | 2002-04-28 | passed | 3.1 | No | 3 | 3 | 3 | 3 | 3 | 3 | N/R | 3 | 3 | N/A
ITG Trunk 3.0 | 2 | 2002-11-11 | 2002-03-01 |  | TBD | NA
Remote Solutions
Remote Office 9150 (SW upissue 1.3.4) | 3 | 2001-12-01 | 2002-03-22 | passed | 2.1 | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3
Remote Office 9150 (SW upissue 1.3.5) |  | 2002-11-01 | 2002-12-13 |  | 4.0 | Yes
Remote Office 9110 (footstand) | 3 | 2001-04-01 | 2001-11-05 | passed | 2.4 | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 |  | 3
Meridian Digital Telephone Internal IP Adaptor | 3 | 2001-04-01 | 2001-11-05 | passed | 2.4 | Yes | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 |  | 3
Remote Office 9115 (external) | 3 | 2001-04-01 | 2001-11-05 | passed | 2.4 | Yes | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 |  | 3
Meridian Digital Telephone External IP Adaptor | 3 | 2001-04-01 | 2001-11-05 | passed | 2.4 | Yes | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 |  | 3
Wireless Solutions
MDECT DMC8 (8 base stn capacity) | 3 | 2001-04-17 | 2001-08-31 | passed | 2.4 | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | N/A | N/A
MDECT_Messaging | 3 | 2001-11-01 | 2002-05-24 | passed | 3.1 | Yes | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | N/A | N/A
MDECT_C4050 Handset | 3 | 2001-07-01 | 2001-10-31 | passed | 2.4 | Yes | 3 | 3 | 3 | N/A | 3 | 3 | N/A | 3 | N/A | N/A
802.11 Wireless Gateway for Meridian 1 | 3 | 2001-05-01 | 2002-11-01 |  | 3.1 | Yes | 3 | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 2 | 2
C4600/C4610E low power b/stations | 3 | 2002-10-01 | 2002-11-01 |  | 4.0 | Yes | N/A | N/A | N/A |  | N/A | 3 | N/A | N/A |  | N/A
C4012 Handset | 3 | 2002-11-01 | Dec wk3 |  | 4.0 | Yes |  | 3 | 3 |  | 3 | 3 | N/A | 3 |  | 2
C4030 Handset | 3 | 2002-11-01 | Dec wk3 |  | 4.0 | Yes |  | 3 | 3 |  | 3 | 3 | N/A | 3 |  | 2
System Management
MDECT OTM Manager | 3 | 2001-04-17 | 2001-08-31 | passed | 2.4 | Yes | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | NA | N/A
OTM 1.2 | 3 | 2001-09-01 | 2002-02-15 | passed | 2.4.14 | Yes | 3 | 3 | 3 | 2 | N/A | 3 | 3 | 3 |  | N/A
OTM 2.0 | 3 | 2002-06-01 | 2002-10-31 | passed | 2.4 | Yes | 3 | 3 | 3 |  | N/A | 3 | 3 | 3 |  | N/A
OTM 2.01 | 3 | 2002-11-01 | 2003-04-01 |  | TBD | Yes | 3 | 3 | 3 |  | N/A |  | N/A |  |  | N/A
Succession CSE
Succession CSE 1000 Rls1.0 | 3 | 2001-04-01 | 2001-07-31 | passed | 2.4 | N/A | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Succession CSE 1000 Rls1.1 | 3 | 2001-09-12 | 2002-03-25 | passed | 3,1 | N/A | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3
Succession CSE 1000 Rls2.0 | 3 | 2002-03-15 | 2002-10-29 |  | 4.0 | N/A | 3
Messaging
Call Pilot 1.07 software | 3 | 2000-03-01 | Aug wk5 | passed | 2.1 | Yes | 3 | 3 | N/A | 3 | N/A | 3 | 3 | 3 | N/A | 3
Call Pilot 2.0 Software | 3 | 2002-06-01 | 2002-10-31 | passed | 4.0 | Yes | 3 |  |  | 2 | N/A
Call Pilot 201i server | 3 |  | 2001-04-01 | passed | 2.2.2 | Yes | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | N/A | N/A
Meridian Mail 13.14 upissue | 3 | 2002-05-01 | 2002-07-29 | passed | N/A | No | 3 | N/A | N/A | N/A | N/A | 2 | N/A | 3 | N/A | N/A
CallPilot Mini Release 1.5 | 3 | 2002-03-01 | 2002-08-30 | passed | 3.2 | No | 3 | 3 | 3 | 2 | N/A
BCM
BCM 2.5 |  | Q2-01 | 2001-09-17 | passed | N/A | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
BCM 2.5 - FP1 | 3 | 2002-02-01 | 2002-04-29 | passed | N/A | Yes | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
BCM 3.0 | 2 | TBD | TBD
Contact Centre Portfolio
SCCS Rls 1.1 incl. GRTD | 3 | 1999-02-01 | 1999-03-01 | passed |  |  | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | 3 | N/R
SCCS Rls 1.5 | 3 | 1999-06-01 | 1999-08-01 | passed |  |  | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | 3 | 3
SCCS Rls 3.0 Nodal | 3 | 1999-10-01 | 2000-04-01 | passed | 2.1 |  | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 2 | 1
SCCS Rls 3.0 Networking | 3 | 1999-11-01 | 2000-04-01 | passed | 2.1 |  | 3 | 3 | N/A | 3 | N/A | 3 | 3 | 3 | 2 | 1
SCCS Rls 4.0 | 3 | 2000-09-01 | 2001-02-14 | passed | 2.3 | Yes | 3 | 3 | N/A | 3 | N/A | 3 | 3 | 3 | 1 | 3
Symposium Config. Tool | 3 | 2000-04-01 | 2000-08-01 | passed |  |  | 3 | N/A | N/A | N/A | N/A | 3 | N/A | 3 | N/A | N/A
Symposium Express CC | 3 | 1999-02-01 | 1999-04-01 | passed | [5 empty] | 1 | N/A | 3 | 3 |  | 3 | 3
SCCS Rls 4.2 | 3 | 2001-10-01 | 2002-04-01 | passed | 3.11 | Yes | 3 | 3 |  |  | N/A | 3 | 3 | 3 |  | 3
SCCS Rls 4.2 CPI | 3 | Q3-2002 | 2002-12-01 |  |  |  | 3
Stratus HA Compatability | 3 | 2002-07-01 | 2002-10-01 | Passed | N/A |  |  | N/A |  |  | N/A |  | N/A | N/A
SCCS Web client 4.0 | 3 | 2001-05-01 | 2001-12-01 | Passed | 2.4 | Yes | 3 | 3 | N/A | 1 | N/A | 3 | 3 | 3 |  | 3
Symposium Express CC 2.0 | 3 | 1999-08-01 | 1999-09-01 | passed | 1.2 | yes | 3 | 3 | 3 | N/A | N/A | 3 | 3 | 3 | 3 | 3
SCCS Web client 4.0 SU05 | 3 | 2002-01-01 | 2002-03-01 | Passed | n/a | Yes | 3 | N/A | N/A | N/A | N/A | 3 | 3 | N/A | N/A | N/A
SCCS Web Client 4.5 | 3 |  | 2003-07-01
Symposium Express CC 3.0 | 3 | 2001-01-01 | 2001-07-26 | Passed | 2.4 | Yes | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 1 | 3
SWRS Rls 1.0 | 3 | 1998-10-01 | PB | [7 empty] | N/A
SWRS Rls 2.0 | 3 | 1998-10-01 | Cont. Rel |  |  |  | 3 | 3 | 2 | 2 | N/A | 3 | 3 | 3 | 3 | 3
Symposium Express 4.2 | 3 |  | 2003-04-01
SWCP 3.0 | 3 | 2001-04-01 | 2002-06-01 | Passed | 2.4 | Yes | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | 3
Symposium Agent Rls 1 | 3 | 1998-11-01 | 1998-12-01 | passed |  | yes | 3 | 3 | 3 | 1 | N/A | 3 | 3 | 3 | 3 | 3
Symposium Agent Rls 1.1 | 3 | 1999-02-01 | 1999-04-01 | passed |  | yes | 3 | 3 | 3 | 1 | N/A | 3 | 3 | 3 | 3 | 3
Symposium Agent Rls 2.0 | 3 | 1999-10-01 | 2000-04-01 | passed |  | yes | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | 3 | 3
SWCP 4.0 | 3 |  | 2003-07-01
Symposium Agent Rls 2.3 | 3 | 2000-11-01 | May wk4-01 | passed | 2.3 | Yes |  |  | N/A |  | N/A | 3
Agent Greeting 2.0 | 3 | 2000-12-01 | 2002-01-31 | passed | 2.3 | Yes | 3 | 3 |  | 3 | N/A |  | 3 | 3
MAX 9 | 3 |  | 1999-10-01 | passed |  |  | 3 | 3 | 3 | 1 | N/A | 3 | 3 | 3 | 3 | 3
MAX 10 | 3 | Q1-01 | 2001-12-01 | passed | 2.3 | No |  |  | N/A | 3 | N/A | 3 | 3 |  | N/A | N/A
MTE 9 | 3 | 1999-03-01 | 1999-04-01 | passed |  |  | 3 | 3 | 3 | 1 | N/A | N/A | N/A | 3 | N/A | N/A
Link-CCR CoRes Rls 6.42 | 3 |  |  | retired |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Symposium Link 6.01 | 3 | Q3 | Controlled Release |  | 2.2.2 |  | 3 |  | N/A | 3 | N/A |  | 3 |  | N/A | N/A
TAPI SP for M1, Rls 2.1 | 3 | 1999-02-01 | 2000-03-01 | passed |  |  | 3 | 3 | 3 | 1 | N/A | 3 | 3 | 3 | N/A | N/A
TAPI SP for M1, Rls 2.2 | 3 | 1999-12-01 | 2000-04-01 | passed | 1.2 |  | 3 | 3 | 3 | 3 | N/A | 3 | 3 | 3 | N/A | N/A
Call Manager PRO | 2 | 1999-04-01 | NA | [6 empty] | 1 | N/A
Desktop TAPI SP2.0 (for MCAs) | 3 | 1999-04-01 | 1999-10-01 | passed |  |  | 3 | 3 | 3 | 1 | N/A | 3 | N/R | 3 | N/A | N/A
Call Pilot | 3 | 1999-03-01 | 1999-08-01 | passed |  |  | 3 | 3 | 3 | 1 | N/A | 3 | #REF! | 3 | 3 | 3
Call Pilot 1.06 Client | 3 | 2000-01-01 | 2000-03-01 | passed |  |  | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
TAPI SP for M1, Rls 2.3 | 3 | 2000-11-01 | 2001-04-30 | passed | 2.3 | Yes |  |  | N/A |  | N/A | 3
TAPI SP Service Update 2.3.1 | 3 | 2002-03-01 | 2002-06-21 | passed | n/a | Yes | 3 | N/A | N/A | 2 | N/A | 2 | N/A | N/A
TAPI SP 3.0 | 3 |  | 2003-07-01
Symposium Communications Driver for Siebel 7 | 3 | 2002-10-01 | 2003-01-01 |  | N/A
MPS100 | 3 | 2002-03-01 | 2002-07-01 | passed | n/a |  | 3 | 3 | 3 | 1 |  | 3 | 3 | 3
Meridian Max 7.52 ( Y2K Upissue) | 3 | 1999-01-01 | 1999-03-01 | passed | [5 empty] | 1 | N/A
Meridian NAC 2.5x (Y2K Upissue) | 3 | 1999-02-01 | 1999-03-01 | passed | [5 empty] | 1 | N/A
Call Recorder (Comverse) | 3 | 2000-02-01 | [8 empty] | N/A
Key:
| N/A or R | = Not applicable or required
= Not scheduled / overdue
= Work in progress
= Complete
| bold | = GA passed
Note on A6: X11 R25 Ref: PBME415; PBME416; PBME417. Support for: M3900 Digital Telephones Phase II, CP Pentium II , Fibre Network Fabric, D-Channel Expansion, 24 Port Digital Line Card, Meridian Integrated ITG 2.0, Business Networking Express, MAT 6.6 & OTM Compliance, Meridian IP, Mobile DECT,Call Centre Agent Greeting
Note on A7: MAT 6.6 Support X.11 rls 25, Win 95/98 & NT 4.0 SP6 NCE (FNF), M3900 series enhancement, ITG IP Phone (ITG Line Card Config & Maint), i2004 (etherset), MDECT (MSMN), FBP Phase II - ISM Enhancements, BNE Phase I/II - NPN, EDIV, ECT, Agent Greeting
Note on A8: MAT 6.6 localised: German and French localised version of MAT 6.6
Note on A9: Unit that enables the extension of office DN and LAN functionality to the home for part time or full time teleworking. Efficient enough to be used for home based call centre agents. Also has an analogue port for fax or analogue telset. Line card in the Meridian 1 links the telephony to an ISDN line connected to the home office unit (Known in the UK as Home Access Terminal (HAT))
Note on A13: BRAnch VOice Ref: PBME 362 Cost effective solution for networking small branch offices. Eliminates need for leased lines. Allows up to three simultaneous voice conversations and their signalling on a single standard ISDN call.
Note on A23: Jim Briscoe: With improved mechanical connection to host set
Note on A24: CPP Increases system real-time capacity. Required For ACD DN expansion on Rls 25.40. EEPE/EPE not supported with CPP
Note on A25: FNF Increases scalability up to 16,000 ports Dual Sonet Ring architecture for enhanced reliability Standard offer for Opt 81 New Systems from NP 2.3
Note on A29: C4040 Docking Station Ref: PBCE51 A desktop unit that converts a C4040 handset into a complete replacement for a desktop hands free telephone. Comprises of a C4040 charger, loudspeaker, microphone and additional speed dial keys in a compact desktop unit.
Note on A30: Administration and Maintenance management tool using a PC running Microsoft Windows.
Note on A31: MDECT Handset superseded by the C4020
Note on A32: Capacity enhancement enables the number of MDECT handsets to be increased on 2 IPE modules from 1024 to over 3000.
Note on A33: DECT CTI Phase I (Alarms Server) Ref PBCE49 CARS (Companion Alarms response Server) is an alarm notification and response application running on a PC server connected to the M1. This enables external events to trigger alerting call to a Companion cordless handset or a digital desktop telset (Aries, Orion or Taurus). Intended primarily for use with DECT, but will operate with both DECT and CT2 versions of Meridian Companion. Also compatible with non-cordless alphanumeric display telephones on Meridian.
Note on A34: MWI (Message Waiting Indicator) was made available with the C4010 handset and this has been carried over to the C4020.
Note on A35: C4010Ex is an intrinsically safe handset for use in potentially hazardous areas. Not suitable for mining but can be used on oil rigs, chemical works etc.
Note on A36: (May 2000) - The generic handset now available for MDECT systems.
Note on A37: Gives the ability to move from ones home MDECT site to a number of other sites with MDECT and use the same handset and extension number. The home system will be informed as to where to redirect calls in the same way as a GSM phone. 1st phase of MSMN necessitates the registering of handsets at each site.
Note on A43: Jim Briscoe: Use '+' to Ungroup Use '-' to Group
Note on A45: OTM 1.0 Product is to be upgraded to 1.01
Note on A46: OTM 1.01: German and French localised version of OTM 1.0 - ALSO bug fix up-issue - supports Windows 2000 - admin for Survivable IP Expansion
Note on A47: Meridian Integrated Telephony Gateway Trunk 2.0: Increasing port capacity to 24 simultaneous calls and adding MCDN and QSIG signalling support
Note on A49: Rls 25.40 Content: Introduces Survivable IP which gives the ability to distribute Option 11C cabinets across a LAN, and to have them "survivable" i.e. if the main cab goes down they can run in standalone mode, and have trunks in them with PSTN access. Networking Enhancement: · Network Break-in and Forced Disconnect M3900 Enhancements: · Full Duplex Hands free (H/W control) · Virtual Office Erase Callers/Redial list · Virtual Office Automatic Logout · Set-to-Set messaging enhancements · System initiated language selection · One-button Feature Access Keys For other features see product presentation. Rkls25.40B Release 25.40 software has been up-issued to address identified SNMP security vulnerabilities identified by CERT®, a federally funded Internet security watchdog organization. There are no keycode impacts to the up-issue.
Note on A50: Rls 26 content New Content to be defined (EPE break)
Note on A51: MIPCD = Meridian Integrated Personal Call Director. One Number / 'Follow Me' functionality based on MICB platform
Note on A52: MIRAN III is an up issue of MIRAN II where we move from ageing VPS platform to new Media Card (SA). With MIRAN III each pack will now have its own IP access and cross connects will be removed in favour of RAN and Music RAN Broadcast features from X11 Rls 23. MIRAN III will replace MIRAN II across all Channels from GA.
Note on A53: MICB III introduces the following new User enhancements: Fast open Internet browser interface for scheduling and administration. New Browser User Interface for Conference Control by chairperson. Acquire/release Chairperson control while in the meeting. Manual gain control by conference participants and Chairperson. Interaction with Meridian-1 Authorization feature for secure Dial Out . Conference specific greetings. Pre-meeting and post-meeting caller notification. Group-call improvement: Smart re-try. Dual card meeting improvement - Chairperson control over Dual Meeting. MICB III introduces the following new Administration enhancements: Brandline greeting recording from a telephone. Customized Login window (BUI). Customized Email format for scheduling notification. Single number access to all meetings - Reduced need for agents Report browsing: viewing reports by BUI. Login passwords security. Automatic backup via email - Back up/restore log MICB III introduces the following new Support enhancements: Ping Client for testing internet connection. CLI command entry direct from BUI. Error handling improvements. Better tracking of log in/out and password access improvements. Debug area password added.
Note on A54: The DDP2 (NT5D97xx) is a dual (two loops) 2.048 Mbps Digital Trunk Interface / Primary Rate Interface pack. It integrates the functionality of a single QPC414 ENET (two terminal loops) and two DTI2 / PRI2 cards on one single CE slot pack. Each of the two DDP2 loops may be independently configured to provide the DTI2 or the PRI2 interface. The DDP2 pack is software compatible with the NTCK43 Dual PRI card. The DPP2 pack is compatible with all Meridian 1 and MSL-1 Large machines (not supported on Option11, 11E or 11C) and can be mixed in the same machine with the earlier DTI2 (QPC536) and PRI2 (NT8D72 & NTCK43) packs.
Note on A57: Smile2 Screen based console. -Completely Revised Screen Layout -Greater use of icons -Easier name searches -Uses an MS Access database instead of Foxpro -Dual language functionality -Customisable languages -Additional Information presented for callers on-hold (waiting time, caller line ID, ) The advanced version of Ascom Smile allows the automatic updating of the local Smile Database from an LDAP database. The Avanced Smile version also allows "networking", whereby a number of Smile consoles share the same database by using periodic synchronising to a server based LDAP database.
Note on A58: M39xx Phase III Note: For support on Remote Office the Remote Office firmware must be 1.3.4 or higher There are two new software packages to enable the M3900 Enhancements in X11 Release 25.40: - Pkg. 386: M3900 Phase III Productivity Enhancements - Set-to-Set Messaging Enhancements - System Initiated Language Selection - One Button Feature Access Keys - Pkg. 387: M3900 Phase III Virtual Office Enhancements - Virtual Office Erase Callers / Redial List - Virtual Office Automatic Logout Note: New part numbers are being introduced to distinguish M39xx phase III
Note on A61: Full Duplex Handsfree (FDHF) Full Duplex Handsfree (FDHF) functionality allows simultaneous two-way communication during a Handsfree call. For Full Duplex Handsfree functionality, you will require a new M3904 phase 3 set equipped with a FDHF cartridge.
Note on A63: Allows single Cat 5 data drop to the desk. Connect i2004 & PC. Delivers power to i2004. Prioritizes voice.
Note on A64: Lan Powering - Inserts power mid span to cat 5 cable drop to desk on unused pairs. 19" rack mountable. Resides in closet. PIPP - Power In-Line Patch Pannel.
Note on A65: i2004 firmware to support 802.1Q on these sets with ITG Line 2.2/Rls 25.15 ahead of availability of IP Line 3.0 Code will be available on the web.
Note on A66: i2004 improvements Phase I: i2004 with integrated 3 port switch, same product functionality as before A Charcoal colured set will also be added to the Portfolio with the introduction of the Phase 1 set (Existing colour being Ethergrey)
Note on A68: A softphone that emulates a i2004 set on a PC , supported using Nortel's USB headset
Note on A69: i2002: Entry level IP set with integrated 3 port switch The i2002 will be available in 2 colours, Charcoal and Ethergrey
Note on A73: IP phone: requires a line card which is based on ITG 2 hardware. It provides support for up to 96 ethersets (24 Ethernet ports on card).
Note on A74: Softphone - Emulates functionality of i2004. NOTE: ITG Line 2.2 up-issue and Rel 25.40 is required to enable the i2050
Note on A75: Includes support of NAT, support of 802.1p/q, corporate directory, the possibility to configure DSPs in non-blocking zones, patchability, and user labelled feature keys Runs on Rls25.15 onwards.
Note on A76: a.k.a ITG Trunk 2.0 on Media Card: New hardware platform for support of the ITG 2.0 trunk functionality. One slot, 32 ports.
Note on A77: This is a update of the ITG Trunk card. It allows a Meridian 1 system to interwork with IP Peer on Succession CSE Rls 2.0 Used on the Meridan side (not the Succession CSE 1000 side)
Note on A80: Note: Remote office Software version 1.3.4 is required to support M39xx phase 3 Remote Office offers the benefits of using Voice over IP to extend the digital telephone across an IP network. They will also provide connectivity over the reliable circuit-switched network by using dial-up ISDN BRI or analog lines.Remote 9150 offers new options for the small branch or remote office environment that desires corporate PBX features and functionality. Up to 32 digital telephones can be extended from the PBX to this remote unit. Remote 9150 unit also supports local calling and local switching.
Note on A81: Note: Remote Office Software version 1.3.5 is a maintenance release of the product so does not involve Type Approvals, re-training etc This release includes support for the Remote Office 911x series units, Meridian Digital Telephone IP Adapter units (Internal and External), M39xx Phase III digital telephone sets, as well as Bridge Port and Differentiated Services (DiffServ) functionality. Major feature enhancements for 1.3.5 V.32 modem support: Remote Office 911x series units offer improved support of V.32 modem calls. Minor feature enhancements for 1.3.5 ! Overlap signaling: Remote Office and the RLC now support overlap signaling for Japan ISDN calls. ! Full Duplex 10-Megabit Ethernet: Remote Office and the RLC now support simultaneous transmission and reception of Ethernet packets. ! Non-linear processing: Remote Office and the RLC now support configuration of non-linear processing (NLP) for enhanced control of echo cancellation. ! Jitter buffer configuration: Remote Office and the RLC now support configuration of the jitter buffer size, enabling you to reduce delay on your Remote Office system.
Note on A82: Single User Remote Office: Remote 9110 is a small circuit board that is mounted in the foot stand of a digital telephone.
Note on A83: Meridian Digital Telephone Internal IP Adaptor: Based on the Single User Remote Office 9110 with analogue port removed Applies to Remote Office only
Note on A84: Single User Remote Office: The Remote 9115 offers the flexibility of a small external enclosure cabled to the digital telephone.
Note on A85: Meridian Digital Telephone External IP Adaptor Based on the Single User Remote Office 9115 with analogue port removed Applies to Remote Office Only
Note on A88: The doubling of the Base Station capacity on the DMC and DMC-E cards means that the customer can use 8 base stations with one DMC card instead of 1.
Note on A89: Short Messaging and Alarms Messaging functionality. Server based application.
Note on A91: Used in conjuction with Symbol handsets for bar code scanning and DECT communications. Handsets will be available from DACON and Symbol. Product Bulletin will contain ordering information.
Note on A92: Both the C4600 and C4610 basestations are being enhanced. The enhancements include the base stations being low powered which will remove the need for local power using transformers. Enhancement to the C4610 will make it the C4610E. The C4610E will have a socket for attaching an external antenna (not supplied by Nortel Networks). Internal Nortel testing will be carried out, no Beta trials will be held. New part numbers will be assigned to the new basestations but there is no difference in DECT functionality. Product Bulletin P-2002-1556-EMEA
Note on A93: djrose: The C4012 handset is an entry level handset being introduced to replace the C4010.
Note on A94: djrose: The C4030 handset is a mid range handset being introduced to replace the C4020.
Note on A97: OTM MDECT Manager enables customers with OTM to administer and maintain the MDECT system from one management terminal.
Note on A98: OTM 1.2: Concurrent release to Rls 25.40
Note on A99: Concurrent release to Succession CSE 1000 Rls 2.0
Note on A100: localised version of OTM 2.0 into French and German, no new functionality
Note on A102: Succession CSE 1000 : Succession CSE 1000 is an enterprise IP telephony solution extending the market-leading Meridian 1 business feature and service capabilities into the next generation of technology -an IP telephony communication server running over a telephony grade,converged network.
Note on A103: Succession CSE 1000 Rls 1.0: Terminals Supported i2004 Taurus M3900 series on Remote Office eMobility 802-11 Wireless LAN DECT Gap compliant sets PC based Attendant Consoles IPE Equipment Supported Primary Rate ISDN (PRI) Analogue Trunk Cards Analogue Line Cards PC Console Interface Unit Card Reach Line Cards for Remote Office MiXX cards (MICB, MIRAN, MIPCD) Integrated Conference Bridge (MICB) Integrated Recorded Announcements (MIRAN) Integrated Personal Call Director (MIPCD) Call Pilot IPE card DECT mobility cards IP Telephony Gateway Line Card 3 x Serial Interface ports Applications Support Call Pilot Unified Messaging DECT Mobility eMobility 802.11 Wireless LAN Symposium Express Call Centre Symposium Call Centre Server Open Interfaces Microsoft TAPI eBusiness Link Symposium Link Services Management Optivity Telephony Manager Networking Support National and Euro - ISDN MCDN - for centralised and/or networked applications: Call Pilot, Symposium, Voicemail, Attendant Services across multiple Succession CSE 1000, Meridian 1, and BCM QSig - open multi-vendor networking standard Comprehensive least cost routing support Seamless end user networking features (e.g. Network ring again, call forward) Power Universal Input (auto-sensing): 85 - 264V AC, 50/60 Hz AC Input: 1 Amp max at 115V AC
Note on A104: Succession CSE 1000 Rls1.1: Adds support for the following products to Rls1.0: - i2050 Softphone - Basic Rate ISDN - DPNSS
Note on A105: Succession CSE 1000 Rls2: New in Rls2: - Peer Networking over WAN - Scales to 1000 Internet telephones per call server - Gatekeeper enables Simplified Numbering Plan (one per network) - Centralized Terminal Proxy Server enables Simplified Engineering/Improved Scalability (one per system) - Will support Nortel H.323 WAN trunk Gateway or 3rd party Gateway* - i2002 Terminals
Note on A111: 201i Server Platform: The 201i platform replaces the 200i platform. It has the following enhancements: * Higher performance processor (Celeron 300A) * 10/100 Base-T Customer LAN (CLAN) replaces the 10 Base-T only CLAN. * 4 Faceplate MPC sockets (8 DSP's) instead of 2 MPC sockets (4 DSP's) * DOS Load now contained in embedded flash. PCMCIA card no longer required. * Ability to connect to two IPE slot DS0's for future capacity enhancements. * New cabling structure * Other Enhancements to installation and maintenance procedures.
Note on A112: Key enhancements on MM13.14 are o 190 Networking sites o 40 Enterprise Networking Channel o Mailbox expiry (90 to 365 days) o Migration utility changes for SCCS prompt o MMR support of Win2K and NT4
Note on A113: CallPilot 150 8 ports / 59 hours (expandable to 82 hours) 20 - 200 mailboxes 0-100 Destop users Automated Attendant Custom Call Routing CallPilot Unified Messaging CallPilot Digital Networking (VPIM, AMIS) Release 1.5 will have localised prompts for a small group of languages.
Note on A128: Symposium Call Center Server offers seamless networking, comprehensive real-time reporting, flexible call handling, and enables advanced eBusiness applications for dynamic contact centers.
Note on A129: SCCS 4.2 CPI is the Call Pilot Integration with SCCS 4.2 and is a post SCCS 4.2 GA introduction
Note on A131: The Symposium Call Center Web Client introduces superior management tools that better equip call center managers to make improved business decisions and respond faster to customer needs, thereby improving productivity and strengthening customer relationships.
Note on A133: Introduces GRTD Enhancements to the existing product
Note on A135: Symposium Express Call Center is an entry level ACD starter product, delivering simplified skill-based routing with sophisticated management reporting wrapped in an easy to use User Interface.
Note on A139: Symposium Web Center Portal empowers businesses with the capability to enhance customer interactions through a management solution that routes, tracks, and reports on electronic inquiries from the enterprise's website.
Note on A144: Symposium Agent is a web technology based software framework that enables call center agents to provide even more intelligent and personalized customer care.
Note on A145: Symposium Agent Greeting is a simple, easy to use solution that enables contact center agents to pre-record standard, or multiple greetings that can be played to each customer before the agent handles the live call. Nortel Networks' Symposium Agent Greeting opens the doors to increase agent satisfaction, agent retention, and customer loyalty.
Note on A147: Meridian Max is a call center management application that responds quickly to fluctuations in call traffic, enables intelligent call assignment, and generates custom reports.
Note on A158: New Functionality SAPphone R/3 compliance Add support for i2004 and i2050 set types (IP contact centre)
Note on A159: JOHNDAVI: key drivers are : Remove the requirement for dongle, Activity codes and Bi-diectional data transfer to IVR
Note on A160: JOHNDAVI: CD will be sold and supported via global Nortel Developer Program Supported with SCCS 4.0 and TAPI SP 2.3.1 and higher versions
Note on A161: Media Processing Server 100 is Nortel Networks’ new Self-Service Portal platform targeted at the Enterprise Contact Centre market and delivered by channel distribution.
Note on D54: GA - Apr 30 2002 and will be introduced into EMEA with FBP 3.1.1 starting May 20.
Note on D64: Apollinaire Moreno: Product currently shipping, awaiting Product Bulletin to declare GA
Note on D89: Apollinaire Moreno: This version on Windows NT4 only David Rose: 3 Jul 2002 update Now being released on W2000.
Note on D91: John Mc Kinnon: Product GA in NA, however, CR status in EMEA.
Note on D139: Jonn Davis: on 28th June Nortel announced the availability of SWCP 3.0 for 50 agents for email & blending. 51-100 agents orders, along with Web Collaboration will remain on controlled release until a customer orders the functionality.
Note on F24: bradleym: 2.2.1 for AOP process. 2.3 for automated process.
Note on F25: bradleym: 2.2.1 for AOP process. 2.3 for automated process.
Note on F37: bradleym: 1.2 for AOP process. 2.2.1 for automated process.
Note on F45: bradleym: 1.2 for AOP process. 2.2.1 for automated process.
Note on F47: bradleym: 1.2 for AOP process. 2.2.1 for automated process.
Note on F57: Orderable using merchandise screen.
Note on F65: Apollinaire Moreno: Code will be available on the web and will be part of IP Line 3.0
Note on F73: bradleym: 2.2.1 for AOP process. 2.3 for automated process.
Note on F77: May not require a tool release (could be a 2.1 replacement). Not yet decided
Note on F150: bradleym: 2.2.2 for AOP process. Not yet automated.
Note on F152: bradleym: 1.2 for AOP process. Not yet automated.
Note on G22: Supported with Remote Office only
Note on G23: Supported with Remote Office only
Note on G58: M39xx is Supported with Remote Office only. M39xx Phase 3 requires Remote Office Rls 1.3.4
Note on G59: PBME: p_2002_1519 M39xx is Supported with Remote Office only. M39xx Phase 3 requires Remote Office Rls 1.3.4
Note on G60: M39xx is Supported with Remote Office only. M39xx Phase 3 requires Remote Office Rls 1.3.4
Note on G61: M39xx is Supported with Remote Office only. M39xx Phase 3 requires Remote Office Rls 1.3.4
Note on G70: Not Applicable ,see line above for status of i2002 on Succession CSE
Note on G77: Used in a Meridian to network with a Succession System (Rls 2.0 onwards).
Note on G139: Will be supported on IP Contact Centre 2.0 in Q4 2002.
Note on G145: Compatible with CSE 1.1
Note on H104: Apollinaire Moreno: Same as for Rls 1.0
Note on I1: an indication of what the pricing of the product will be, used for business plan justification
Note on I100: no changes from OTM2.0
Note on J1: Nortel Networks: Where product fits in current portfolio
Note on J104: Apollinaire Moreno: Same as for Rls 1.0
Note on K1: Supportability, maintainability, for example can the product be remotely supported, what are the Installation times…
Note on M49: PBME 537 Release 25.40 PBME542 Option 11C Survivable IP Expansion Euro Line Up Document PBME540 Option 51C and 61C EMEA Packaging for X11 Release 25.40 and Net Price 3.1 PBME541 Option 81C EMEA Packaging for X11 Release 25.40 and Net Price 3.1
Note on M51: Product Bull
Note on M52: Product Bulletin PBME 557
Note on M53: Product Bulletin: PBME 563
Note on M54: Product Bulletin PBME 558, Meridian 1 Dual PRI/DTI (DDP2)
Note on M57: Product Bulletin PBME 556
Note on M58: PBME 538: Introduction of M3902-M3904 Phase 3 PBME 539: Introduction of M3905 Phase 3 PBME 545: Introduction of M3900 PC-Utility and TAPI 2.1 SW
Note on M59: P-2002-1519: Introduction of the ATA for M3904
Note on M60: PBME 545: Introduction of M3900 PC-Utility and TAPI 2.1 SW
Note on M61: PBME538: Introduction of the M3902-4 Phase 3
Note on M63: PBME 524: Introduction Internet Telephony Switch Module PBME 562: IP Contact Centre using i2004/i2050
Note on M64: PBME 546: Introduction Power Inline Patch Panel
Note on M73: PBME 481: Introduction ITG Line 2.0 & i2004 PBME 553: Introduction ITG Line 2.2 & i2050 with i2004 enhancements PBME 562: Using i2050 & i2004 in Call Centers
Note on M74: PBME 553: Introduction ITG Line 2.2 & i2050 with i2004 enhancements PBME 554: Update ITG Line 2.2 & SNMP vulnerability PBME 562: Using i2050 & i2004 in Call Centers
Note on M76: PBME 452: Introduction ITG Trunk 2.0 PBME 497: ITG Trunk 2.xx.24 SW-upissue PBME 547: ITG Trunk 2.xx.25 SW-upissue PBME 552: Introduction ITG Trunk 2.1 on Media Card platform PBME 555: Notice of retirement ITG Trunk 486 & pentium cards
Note on M80: Product Bulletin: PBME 521 RO 1.3.1 Detailed bulletin PBME 548 RO 1.3.4 upissue
Note on M82: PBME548: Remote Office 911x Rel 1.3.4
Note on M84: PBME548: Remote Office 911x Rel 1.3.4
Note on M92: P-2002-1556 EMEA: New MDECT Basestations
Note on M93: P-2002-1547 EMEA: Changes to the MDECT handset portfolio
Note on M94: P-2002-1547 EMEA: Changes to the MDECT handset portfolio
Note on M97: PBCE 69: OTM-DECT & DMC8 Introduction PBCE 70: OTM-DECT & DMC8 Lab Kit PBCE 76: OTM-DECT & DMC8 General Release
Note on M98: PBME 531: Support Limitations for OTM on Windows 95 PBME 535: Introducing OTM 1.2 P0945877: General Release Bulletin OTM 1.2 PB 2002-061: OTM CPND Product Advisory
Note on M99: GR-2002-1559 General Release Bulletin OTM 2.0
Note on M103: PBME 509 Availability of Succession CSE Rls1.0
Note on M104: PBME 543 Introduction of Succession CSE 1000 Rls1.1
Note on N1: Are training courses available. (Details added to training tracker work sheet)
Note on N6: Hermann Obermaier: Also available in German language. Please see training Details.
Note on N74: Apollinaire Moreno: i2050 included in general ITG Line /i2004 Tech Training
Note on N82: PBT available for GA
Note on N104: Apollinaire Moreno: Same as for Rls 1.0
Note on O104: Apollinaire Moreno: Available in Netprice 3.1 price book
Note on P1: Channel Marketing able to support distributors with their sales training.
Note on P73: Apollinaire Moreno: IP Line included in general Meridian and Succession Sales Training
Note on P74: Apollinaire Moreno: i2050 included in general Meridian and Succession Sales Training
Note on P104: Apollinaire Moreno: Same as for Rls 1.0
Note on Q1: availability of sales materials such as brochures, flyers on the product.
Note on Q74: Apollinaire Moreno: i2050 included in general Meridian and Succession Brochures
Note on Q104: Apollinaire Moreno: Same as for Rls 1.0
Deliverables
Products
Note: The dates shown are the Nortel Networks product readiness dates,
please contact your Channel NPI/PM prime for individual Channel General Availability Dates!

## Revision History
Spreadsheet | Updated by | Date | Reason
Master NPI Status | John Davis | 2002-01-10 | SCCS R4.2 CPI program added
Master NPI Status | John Davis | 2002-01-10 | TAPI 2.3.1 service update added
Master NPI Status | John Davis | 2002-01-10 | SWCP3.0 Controlled Release date changed to February 2002, further trialing of Service Update (PEP7) required.
Master NPI Status | Jim Briscoe | 2002-01-15 | Changed Net Price Portfolio of Products GA date drom Feb 22nd to Mar 25th
Training Details | Apollinaire Moreno | 2002-01-17 | Updated ITG Trunk 2.0 and i2004 Training details with course 25096A, "IP Telephony Gateway 2.0 (Trunk & LineSide/i2004)"
Master NPI Status | Apollinaire Moreno | 2002-01-17 | Updated Succession CSE 1000 Rls2.0 Beta (March 2002) and GA (Q3 2002) dates.
Master NPI Status | Donall O'Murchu | 2002-01-18 | Moved the ITG2.1 Trunk GA from Feburary to early March.
Master NPI Status | Donall O'Murchu | 2002-01-22 | Extra lines added to the comment on Smile2 detailing the additional features available in the advanced version as opposed to the standard version.
Master NPI Status | John Davis | 2002-01-24 | FBP rls changed to 3.11 in May timeframe
Master NPI Status | John Davis | 2002-02-07 | Sympsoium Agent Greeting 2.0 passed GA on January 25th 2002
Master NPI Status | John Davis | 2002-02-07 | SWCP3.0 Controlled Release date changed to March 2002, further trialing of Service Update (PEP7) required.
Training Details | John Davis | 2002-02-07 | Training details added for Symposium Web Client
Master NPI Status | Rick Cross | 2002-02-07 | Wireless VoIP GA date 30 March 2002
Master NPI Status | Jim Briscoe | 2002-02-08 | MDECT Messaging GA date changed to April
Master NPI Status | Jim Briscoe | 2002-02-08 | OTM GA Date prought forward to Feb 15th from Mar 25th. Changed Order tool from NP 3.0 to NP 2.4.14
Master NPI Status | Jim Briscoe | 2002-02-08 | Changed Remote Office to show the software upissue 1.3.4 GA Date. This is required for M39xx Phase III support
Master NPI Status | Donall O'Murchu | 2002-02-08 | Changed MIRAN 3 GA date to March 8th.
Master NPI Status | Donall O'Murchu | 2002-02-08 | Added coment to the Smile2 GA date detailing that the product is now available to order on a controlled Release basis.
Master NPI Status | Donall O'Murchu | 2002-02-14 | Changed Smile 2 GA date to 21st March 2002
Master NPI Status | Donall O'Murchu | 2002-02-15 | Addded MICB III with a GA date of June '02
Master NPI Status | Donall O'Murchu | 2002-02-19 | Changed the GA Date for the DDP2 pack from "TBD" to mid-April.
Master NPI Status | John Davis | 2002-02-20 | Netprice versions added for Messaging portfolio
Master NPI Status | John Davis | 2002-02-20 | MPS 100 Beta and GA dates updated
Master NPI Status | John Davis | 2002-02-20 | Symposium Web client Rls 4 SU05 added
Documentation | Kirsty Halloran | 2002-02-20 | Added documentation tab with internet download instructions
Master NPI Status | Apollinaire Moreno | 2002-02-20 | Added comment to indicate that the PIPP is currently shipping and awaiting the availability of the Product Bulletin to be declared GA - Product Bulletin now red flag.
Master NPI Status | Apollinaire Moreno | 2002-02-20 | Type Approval for Succession CSE 1000 now green, as completed for most countries where Nortel operates.
Master NPI Status | Jim Briscoe | 2002-02-20 | Changed GA date for Remote Office 1.3.4 to 20th of March
Master NPI Status | Burckhardt Emons | 2002-03-13 | Changed GA date for MM13.14 to 30th of May
Contacts | Burckhardt Emons | 2002-03-13 | Changed PLM contact for MM13.14
Master NPI Status | Donall O'Murchu | 2002-03-13 | Changed E-Mobility Gateway GA date to End April.
Master NPI Status | Donall O'Murchu | 2002-03-13 | Moved ITG Trunk 2.1 GA date out to April 5th.
Master NPI Status | Apollinaire Moreno | 2002-03-13 | Removed the Network Energy Source as this product will not be developped by Nortel
Master NPI Status | Apollinaire Moreno | 2002-03-13 | Power In Line Patch panel Product Bulletin now available
Master NPI Status | John Davis | 2002-03-14 | Changed GA date for SWC Service update SU05 to Mar due to delays to availability of the update.
Master NPI Status | John Davis | 2002-03-14 | Changed GA date for SCCS CPI to Q4 2002
Master NPI Status | Donall O'Murchu | 2002-03-14 | Moved MIRAN III GA date out to April 5th.
MPOR SENT 15/03/02
Master NPI Status | F Frizzarin | 2002-03-22 | Moved the CP2.0 Beta to June 02 and the GA to 31st Oct 02
Master NPI Status | Apollinaire Moreno | 2002-04-03 | Final pricing now available in the Netprice 3.1 price book for Succession CSE 1000 and i2050
Master NPI Status | Jim Briscoe | 2002-04-03 | Remote Office 1.3.4 GA (M39xx Phase III support)
Master NPI Status | Jim Briscoe | 2002-04-03 | OTM 2.0 Beta date changed to June 02
Master NPI Status | Jim Briscoe | 2002-04-03 | MIRAN III GA date changed to May 31st
Master NPI Status | John Davis | 2002-04-04 | Symposium Web Client Service update (SU05) passed on March 20th
Master NPI Status | John Davis | 2002-04-04 | Symposium Web Centre Portal completed trial for 15-25 agents with email & blending on April 3rd.
Master NPI Status | Donall O'Murchu | 2002-04-04 | Moved ITG2.1 GA date out to April 30th
Master NPI Status | Donall O'Murchu | 2002-04-04 | Moved Smile 2 GA date out to May 2002.
Master NPI Status | Donall O'Murchu | 2002-04-04 | Added NetPrice 3.1.1 as the NetPrice release date for the DDP2 pack.
MPOR SENT 05 /04/02
Training Details | David Rose | 2002-04-08 | URL for Nortel Networks Knowledge Services changed to www.nortelnetworks.com/training for both the web site and PBT/TBT ordering.
Training Details | David Rose | 2002-04-10 | DECT Messaging training specified as PBT. Course number 35873 This will be available by the end of April.
Master NPI Status | Jim Briscoe | 2002-04-16 | Rls 26 GA date changed to TBD
Master NPI Status | David Rose | 2002-04-25 | MDECT Messaging GA changed to 24 May due to trial site delays.
Master NPI Status | John Davis | 2002-04-26 | SCCS R4.2 Passed GA on 25th April
Master NPI Status | John Davis | 2002-04-26 | TAPI 2.3.1 service update delayed to May due to trial coverage.
Master NPI Status | John McKinnon | 2002-04-26 | 802.11 GA date changed to August'02 for EMEA
MPOR SENT 26/04/02
Master NPI Status | F Frizzarin | 2002-05-14 | GA date for CallPilot Mini 1.5 changed to July 02
Master NPI Status | Apollinaire Moreno | 2002-05-15 | Update following i2050 deliverables: Sales Training, Collaterals, FBP Rls, Tech Training
Master NPI Status | John McKinnon | 2002-05-15 | BCM FP1 - Passed GA 29 April
Master NPI Status | John McKinnon | 2002-05-16 | DDP2 GA date moved out to 20th May to coincide with FBP 3.1.1
Master NPI Status | Joerg Kirmes | 2002-05-16 | OTM 2.0 GA date changed to Oct 02
Master NPI Status | Joerg Kirmes | 2002-05-16 | OTM 2.01 (localised version) GA date changed to Q1 2003
Contacts | Joerg Kirmes | 2002-05-16 | Added PLM contact for OTM 2.0
Training Details | Joerg Kirmes | 2002-05-16 | Updated Training Info for OTM 1.2
MPOR SENT 17/05/02
Master NPI Status | David Rose | 2002-05-30 | MDECT Messaging GA passed 24 May.
Master NPI Status | David Rose | 2002-05-30 | Taurus Phase 3 sets GA passed 25 May
Master NPI Status | David Rose | 2002-05-30 | Taurus FDHF & CTIA GA passed edited to 25 March
Master NPI Status | David Rose | 2002-05-30 | Taurus ATA expected availability moved to 30 June. All EMC testing has passed and move of date is to allow for production rampup
Master NPI Status | John Davis | 2002-05-30 | TAPI 2.3.1 service update delayed to Mid-June due to trial coverage.
Master NPI Status | Joerg Kirmes | 2002-05-31 | OTM 2.01 Beta date changed to Nov 2002, GA date April 2003
Master NPI Status | Apollinaire Moreno | 2202-05-31 | Changed disposition of products, grouping them by category for improved reading
Master NPI Status | Apollinaire Moreno | 2202-05-31 | Added several new products: IP Line 3.0, i2004 Improvements Phase I and II, 802.1Q on i2004
Master NPI Status | Apollinaire Moreno | 2202-05-31 | Added Beta and GA dates for IP Line 3.0
MPOR SENT 03/06/02
Training Details | David Rose | 2002-06-05 | MDECT Messaging CD-ROM training available (course 35873)
Master NPI Status | David Rose | 2002-06-05 | MIRAN III GA passed 31 May.
Master NPI Status | Burckhardt Emons | 2002-06-06 | MM13.14 GA date delayed into June due to delayed start of trials
MPOR SENT 14/06/02
Master NPI Status | Burckhardt Emons | 2002-06-25 | TAPI 2.3.1 GA passed on 21.6.02
Master NPI Status | Apollinaire Moreno | 2002-06-28 | Update status of some Succession CSE 1000 rsl 2.0 deliverables: Pricing and Training
Master NPI Status | Apollinaire Moreno | 2002-06-28 | GA of firmware for support 802.1Q on i2004 and IP Line 2.2 is now August 9th 2002
Training Details | Apollinaire Moreno | 2002-06-28 | Update details on Succession CSE 1000 and IP Line 2.2
Documentation | Kirsty Halloran | 2002-07-01 | Changed instructions to downloading on-line documentation
Master NPI Status | David Rose | 2002-07-03 | C4600/C4610E low power b/stations added to the Wireless section with expected GA date of October.
Training Details | Apollinaire Moreno | 2002-07-03 | Updated Training details for the following products: ITG trunk, IP Line and i2004, Succession CSE 1000 Rls2.0
Master NPI Status | Burckhardt Emons | 2002-07-03 | Changed GA date of Mail 13.14 as GA meeting planned for WK26 has been postponed.
Master NPI Status | Jim Briscoe | 2002-07-04 | Added Product Bulletin to MIC/Product Bulletin Column in comment fields
Master NPI Status | Jim Briscoe | 2002-07-04 | Removed Channel Impact Guidelines Column (as discussed on EoroDac conf Call)
Revision History | Jim Briscoe | 2002-07-04 | Removed Revision History pre 2002
Master NPI Status | John Davis | 2002-07-04 | SWCP 3.0 PASSED GA 28th June
Master NPI Status | Jim Briscoe | 2002-07-05 | Changed MICB III GA date to July 8th
Master NPI Status | John Davis | 2002-07-05 | Added Symposium Web Centre Portal 4.0
Master NPI Status | John Davis | 2002-07-05 | Added Sympsoium Express 4.2
Master NPI Status | John Davis | 2002-07-05 | Added Stratus HA compatability
Master NPI Status | Burckhardt Emons | 2002-07-16 | Changed MM13.14 GA Date to July 29th. Issue with SL100 Site encountered
Master NPI Status | john Davis | 2002-07-26 | MPS100 Passed GA - July 18th
Master NPI Status | F Frizzarin | 2002-07-26 | Changed CallPilot Mini 1.5 GA to 30th August due to a faulty hardware component on the exisiting systems and delays to NetPrice 3.2 roll out
MPOR sent 29/07/02
Master NPI Status | F Frizzarin | 2002-07-30 | Changed the FBP release for CP2.0 to 4.0
Master NPI Status | Apollinaire Moreno | 2002-08-02 | Updated Succession CSE 1000 RLS 2.0 GA from Q3 2002 to October 29 2002
Master NPI Status | Burckhardt Emons | 2002-08-16 | MMR 13.14 passed GA on 29.7.02. GRB bulletin underway
Master NPI Status | Kirsty Halloran | 2002-08-23 | ITG Trunk 3.0 programme added to NPI Status sheet.
Master NPI Status | john Davis | 2002-08-23 | 802.1Q on i2004 delayed to Sept week 1 due to a new bug
MPOR sent 27/08/02
Master NPI Status | David Rose | 2002-08-30 | Smile 2 updated to reflect the GA announced in April 02.
Master NPI Status | David Rose | 2002-08-30 | Taurus ATA passed GA 23 August 2002
Master NPI Status | Frederic Frizzarin | 2002-08-30 | CallPilot Mini 1.5 passed GA on 30 August 2002
Master NPI Status | Kirsty Halloran | 2002-08-30 | Release 25.40B passed GA August 26th
Master NPI Status | john Davis | 2002-09-11 | Added Siebel Communications driver for Siebel 7
Master NPI Status | Jim Briscoe | 2002-09-12 | Updated GA date for ITG trunk 3.0 to Feb 03
Master NPI Status | David Rose | 2002-09-12 | 802.11 Wireless Gateway for Meridian 1 GA changed to TBD
Master NPI Status | David Rose | 2002-09-12 | C4600/C4610E low power b/station GA changed to TBD
MPOR sent 13/09/02
Master NPI Status | john Davis | 2002-10-03 | TAPI SP 3.0 added
Master NPI Status | David Rose | 2002-10-04 | C4012 and C4030 handsets added with Beta Nov and GA Dec wk3, plus training details updated.
Master NPI Status | David Rose | 2002-10-04 | 802.1Q now GA
Master NPI Status | David Rose | 2002-10-04 | i2002 on M11/M1 Beta Nov wk1
Master NPI Status | David Rose | 2002-10-04 | IP Line 3.0 FBP Release NP 4.0
MPOR sent 04 Oct 02
Master NPI Status | Jim Briscoe | 2002-10-14 | Added Product Bulletin Number to comment field for ATA
Master NPI Status | David Rose | 2002-10-17 | 802.11 Wireless Gateway for Meridian 1 GA set from TBD to Nov 02
Master NPI Status | David Rose | 2002-10-17 | C4600/C4610E low power b/stations GA set from TBD to Nov 02 and bulletin has been issued. (P-2002-1556-EMEA)
MPOR sent 18 Oct 02
Master NPI Status | Frederic Frizzarin | 2002-10-31 | CallPilot 2.0 reached GA on 31st October 2002
Master NPI Status | Frederic Frizzarin | 2002-10-31 | Updated Training information for CallPilot 2 and CallPilot Mini 1.5
Master NPI Status | Kirsty Halloran | 2002-11-06 | ITG Trunk 3.0 trials starting Nov 11. GA scheduled for March 21st 03
Master NPI Status | Apollinaire Moreno | 2002-11-06 | Succession CSE 1000 Rls2.0 passed GA on 29th October
Master NPI Status | Joerg Kirmes | 2002-11-07 | OTM 2.0 reached GA on 31st October 2002
Master NPI Status | Joerg Kirmes | 2002-11-07 | Added Product Bulletin Number to comment field for OTM2.0
Master NPI Status | john Davis | 2002-11-08 | SCCS Web Client 4.5 added
Master NPI Status | john Davis | 2002-11-08 | Stratus HA Compatability is now available on SCCS R4.2
Master NPI Status | Maureen Trevethan | 2002-11-08 | i2002 IP Phone passed GA 29th October
Master NPI Status | John McKinnon | 2002-11-08 | IP Line 3.0 passed GA on 31st October'02
Master NPI Status | John McKinnon | 2002-11-08 | Remote Office Maintenance Release 1.3.5 added.
MPOR sent 8 Nov 02

## Contacts
| Nortel | Nortel
| Product Marketing | PLM
Meridian 1
Products GA in 1999-Q2 2001
X.11 Release 25.15 | Hugh Mahony | Fiona Hargaden
MAT Rls 6.6 |  | Eamonn Noone
MAT Rls 6.6 (German/French) |  | Eamonn Noone
Meridian HomeOffice II |  | Eamonn Noone
MIRAN II |  | Ger Kelly
MICB II |  | Ger Kelly
ITG Rls 1 |  | Brendan Noonan
BRAVO I |  | Enda Mongan
X.11 Release 24B |  | Fiona Hargaden
Option 11C Mini |  | Richard Howard
Option 11C LSE Phase 1 |  | Richard Howard
MAT Rls 6.5 |  | Eamonn Noone
Meridian Set M39xx Ph. 1 |  | Maureen Trevethan
Orion ATA (Analogue Terminal Adapter) |  | Maureen Trevethan
CP4 (68060) |  | Enda Mongan
i1010 IP Telecommuter |  | Tom Mcguire
M39xx Display Based Module | Hugh Mahony | Maureen Trevethan
M39xx Key Based Expansion Module | Hugh Mahony | Maureen Trevethan
Option 81C CP Pentium II |  | Enda Mongan
Fibre Network Fabric (FNF) |  | Enda Mongan
MDECT
MDECT C4040 Docking Station |  | Tony Wallbank
MDECT Windows Manager |  | Rick Cross
MDECT C4010 Handset |  | Tony Wallbank
MDECT Capacity Enhancement |  | Rick Cross
MDECT CTI Phase 1 (Alarms Sever) |  | Tony Wallbank
MDECT MWI |  | Rick Cross
MDECT 4010Ex (Int safe h/set) |  | Tony Wallbank
MDECT 4020 (handset) |  | Tony Wallbank
MDECT 2000 (MSMN) | Hugh Mahony | Rick Cross
Products GA in 1999-Q2 2001 | Use '+' to UnGroup and '-' to Group
Products GA for 2001/2002
Meridian 1 Core
Rls 25.40 | Hugh Mahony | Fiona Hargaden
Rls 26 | Hugh Mahony | Fiona Hargaden
MIPCD | Chantal Smith | Ger Kelly
Miran III | Chantal Smith | Ger Kelly
MICB III | Chantal Smith | Ger Kelly
DDP2 - PRI2/DTI pack replacement |  | Don MacRae
Terminals and Accessories
Ascom Smile2 |  | Ger Kelly
Meridian Set M39xx Phase 3 | Hugh Mahony | Maureen Trevethan
M39xx ATA (Analogue Terminal Adapter) | Hugh Mahony | Maureen Trevethan
CTIA (Rls 25.40 dependant) | Hugh Mahony | Maureen Trevethan
Full Duplex Handsfree (FDHF) | Hugh Mahony | Maureen Trevethan
i2004 IP Set | Hugh Mahony | Maureen Trevethan
Internet Telephony Switch Module | Hugh Mahony | Maureen Trevethan
Power In-Line Patch Panel | Hugh Mahony | Maureen Trevethan
802.1Q on i2004 | Hugh Mahony | Maureen Trevethan
i2004 improvements - Phase I | Hugh Mahony | Maureen Trevethan
i2004 improvements - Phase II | Hugh Mahony | Maureen Trevethan
i2050 Softphone |  | Maureen Trevethan
IP Telephony on Meridian 1
IP Line 2.1 and i2004 IP Set | Hugh Mahony | Mike Halligan
IP Line 2.2 and i2050 softphone | Hugh Mahony | Mike Halligan
IP Line 3.0 | Hugh Mahony | Mike Halligan
ITG Trunk 2.1 | Hugh Mahony | Brendan Noonan
Remote Solutions
Remote Office 9150 (SW upissue 1.3.4) | Brigitte Bachecongi | Mike Halligan
Remote Office 9110 (footstand) | Brigitte Bachecongi | Mike Halligan
Meridian Digital Telephone Internal IP Adaptor | Brigitte Bachecongi | Mike Halligan
Remote Office 9115 (external) | Brigitte Bachecongi | Mike Halligan
Meridian Digital Telephone External IP Adaptor | Brigitte Bachecongi | Mike Halligan
Wireless Solutions
MDECT DMC8 (8 base stn capacity) | Hugh Mahony | Rick Cross
MDECT_Messaging | Hugh Mahony | Tony Wallbank
MDECT_C4050 Handset | Hugh Mahony | Tony Wallbank
MDECT C4012 Handset | Hugh Mahony | Tony Wallbank
MDECT C4030 Handset | Hugh Mahony | Tony Wallbank
802.11 Wireless Gateway for Meridian 1 | Hugh Mahony | Rick Cross
System Management
MDECT OTM Manager | Hugh Mahony | Rick Cross
OTM 1.2 |  | Eamonn Noone
OTM 2.0 |  | Eamonn Noone
OTM 2.01 |  | Eamonn Noone
Succession CSE
Succession CSE 1000 Rls1.0 | Paul Rowe | Stephen McCormack
Succession CSE 1000 Rls1.1 | Paul Rowe | Richard Howard
Succession CSE 1000 Rls2.0 | Paul Rowe | Stephen McCormack
Messaging
Call Pilot 2.0 | Chantal Smith | Paul Bree
Call Pilot Mini 1.5 | Chantal Smith | Bill Buckley
Meridian Mail 13.14 upissue | Chantal Smith | Paul Bree
CallPilot Mini Release 1.5 | Chantal Smith | Bill Buckley
BCM
BCM 2.5 | Keith Newman | John Rouette
BCM 2.5 - FP1 | Keith Newman | John Rouette
Contact Centre Portfolio
SCCS Rls 1.1 incl. GRTD |  | Andy Perin | System Management
SCCS Rls 1.5 |  | Andy Perin | MDECT OTM Manager
SCCS Rls 3.0 Nodal |  | Andrew Perrin | OTM 1.2
SCCS Rls 3.0 Networking |  | Andrew Perrin | OTM 2.0
Symposium Config. Tool |  | Donall McNelis | OTM 2.01
Symposium Express CC | Paul Rowe | Morag Kelly
SCCS 4.2 |  | Dara Hennesy
Symposium Config. Tool |  | Donald McNelis
SCCS 4.2 CPI |  | Dara Hennesy / Paul Bree
Symposium Express CC 2.0 |  | Dara Hennesy
Stratus HA Compatability |  | Dara Hennesy
SCCS Web client 4.0 |  | Ifran Ali
Symposium Express CC 3.0 |  | Dara Hennesy
SWRS Rls 1.0 |  | Dave Ray
SWRS Rls 2.0 |  | Nick George
Symposium Agent Rls 1 | Paul Rowe | Paula O'Connor
Symposium Agent Rls 1.1 | Paul Rowe | Paula O'Connor
Symposium Agent Rls 2.0 |  | Paula O'Connor
Symposium Express 4.2 |  | Dara Hennesy
Agent Greeting 2.0 |  | Dave Murray
MAX 9 |  | John Wall
MAX 10 |  | Nick George
MTE 9 |  | John Wall
Link-CCR CoRes Rls 6.42 |  | John Wall
Symposium Link 6.01 |  | John Wall
TAPI SP for M1, Rls 2.1 | Paul Rowe | Paula O'Connor
TAPI SP for M1, Rls 2.2 |  | Paula O'Connor
Call Manager PRO | Paul Rowe | Eamonn Noone
Desktop TAPI SP2.0 (for MCAs) | Paul Rowe | Eamonn Noone
Call Pilot | Hugh Mahoney | Bill Buckley
Call Pilot 1.06 Client | Hugh Mahoney | Bill Buckley
Symposium Agent 2.3 |  | Martin Walker
Symposium TAPI 2.3 |  | Martin Walker
Symposium Web Centre Portal 3.0 |  | Ifran Ali
Meridian Max 7.52 ( Y2K Upissue) |  | John Wall
Meridian NAC 2.5x (Y2K Upissue) |  | John Wall
Call Recorder (Comverse) |  | Mike Healy
Symposium Web Centre Portal 4.0 |  | Ifran Ali
MultiMedia Web API | Paul Rowe | Thomas McGuire
MPS100 |  | John Wall
Products
Contacts

## Training Details
| Technical Training (input to NPI Status sheet col. W) | Available | Training format | Course title / order code / duration
Nortel
NPI
Meridian 1
Products GA in 1999-Q2 2001
X.11 Release 25.15 | 3 | 2000-06-01 | Leader led: (for people looking for hands-on like those having no lab system, especially with CPP and FNF) Leader led: (for people looking for hands-on like those having no lab system) Paper based: | Meridian 1 Upgrade Release 24 to 25 Software and Hardware / course 25645 / 2 days For German Training course 25645 please see: http://www.nortel-dasa.de/eng/catalog/Catalog_Enterprise.html - follow Link "List of Courses" Meridian 1 Upgrade Release 24 to 25 Features and 3900 sets / course 25646 / 1 day For German Training course 25646 please see: http://www.nortel-dasa.de/eng/catalog/Catalog_Enterprise.html - follow Link "List of Courses" Meridian 1 Upgrade Release 24 to 25 / course 25647 For German Training course 25647 please see: http://www.nortel-dasa.de/eng/catalog/Catalog_Enterprise.html - follow Link "List of Courses"
MAT Rls 6.6 |  | June 00, PBT July 00 | 1. First Introduction: 25404 MAT 6.6 Installation and Administration, leader led course 2. Upgrade from MAT 5.7: 25405 MAT 5.7 to 6.6 Conversion and Update, leader led course 3. Upgrade from MAT 6.1 or 6.5: NTPs or GRB are sufficient | 25404 Meridian Administration Tool 6.6 Installation and Administration, 4 days, LL 25405 MAT 5.7 to 6.6 Conversion and Update, 1 day, LL For German Training courses please see: http://www.nortel-dasa.de/eng/catalog/Catalog_Enterprise.html - follow Link "List of Courses"
MAT Rls 6.6 (German/French)
Meridian HomeOffice II |  | 2000-09-01 | OTM Installation (5 days - Leader Led): OTM Basics OTM End User and Server Installation OTM Window Services OTM Web Services OTM Telephony Billing Services (3 days - Leader Led): Overview of TBS Integration with OTM Data collection strategies and methods (DBA, serial, etc...) Basic end user training Costing model configuration Rate tables and location books (including web access to updates) | OTM Installation - 35137 - 5 days - LLT OTM Billing - 35134 - 5 days - LLT MLV or Hoofddorp OTM Installation 25-Sept 13-Nov 11-Dec OTM Billing 18-Sept 8-Nov 18-Dec MOP OTM Installation 25-Sept 6-Nov 4-Dec OTM Billing 13-Nov
MIRAN II | 3 | Yes | NTPs sufficient for distributors upgrading from MIRAN I, else use PBT. | MIRAN Course 25066 (PBT). PBT is an upgrade course only for Miran1 trained people. People new to Miran need to attend the Miran Leader Led course. Course number 25063
MICB II | 3 | Yes | NTPs sufficient for distributors upgrading from MICB I, else use PBT . | MICB Course 25064 (PBT) -
ITG Rls 1 | 3 | 1999-06-01 | Instructor-led training, 3 days | Replaced By ITG 2 course
BRAVO I | 3 | Yes | Instructer-led training . This course carries pre-requisite courses of Meridian 1 Network Installation and Maintenance, and Meridian 1 Networking Dial Plans | Course Number 25075 Meridian BRAnch VOice (BRAVO) Installation & Maint -
X.11 Release 24B | 3 | 1999-08-01 | Paper Based Training if upgrade from Rls 23. | X11 Core Release 23 to 24 Course 25028 (PBT) X11 Networking Release 23 to 24, Course 25027 (PBT)
Option 11C Mini | 3 | 1999-08-01 | PBT, need Rls 24 and MAT 6.5 | Option 11 Mini, Course 25031 (PBT)
Option 11C LSE Phase 1 | 3 | 1999-08-01 | PBT, need Rls 24 and MAT 6.5 | Option 11C LSE, Course 25032 (PBT)
MAT Rls 6.5 | 3 | 1999-08-01 | Recommended but not compulsory if upgrading from 5.7 or 6.1 . 1 day if upgrade from 5.7. If not, instructor-led training course, 4 days. | Meridian 1 Administration Tool (MAT) 5.x to 6.5 Upgrade Course 25414 (1 day) , Meridian 1 Administration Tool 6.5 End-user Course 25433 (2 days) , MAT 6.5 Installation and Administration Course 25403 (4 days)
Meridian Set M39xx Ph. 1 | N/R | 1999-08-01 | Not required, user guide is sufficient. See M39xx Ph. 2 for end user training.
Orion ATA (Analogue Terminal Adapter) | N/R | 1999-07-01 | Not required, installation guide is sufficient.
CP4 (68060) | N/R | 1999-08-01 | Not required, installation guide is sufficient.
i1010 IP Telecommuter | 3 | 1999-07-01 | Instructor-led training, 1 day following ITG Rls1 training (which is a pre-requisite). | IP Telecommuter Release 1, course 25110
M39xx Display Based Module |  | 2000-06-01 | Included in release 25 training | Meridian 1 Upgrade Release 24 to 25 Software and Hardware / course 25645 / 2 days
M39xx Key Based Expansion Module |  | 2000-06-01 | Included in release 25 training | Meridian 1 Upgrade Release 24 to 25 Software and Hardware / course 25645 / 2 days
MDECT
MDECT C4040 Docking Station | N/R | 1999-06-01 | Not required, user guide is sufficient.
MDECT Windows Manager | N/R | 1999-03-01 | Covered in DECT training
MDECT Capacity Enhancement | N/R | 1999-08-01 | Not required, part of Rls 24
MDECT CTI Phase 1 (Alarms Sever) |  | 2000-06-01 | PBT | Companion Alarms Response Server / 35872
MSMN |  | 2000-07-01 | PBT | Multi Site Mobility Networking and Concentration / 35871
MDECT Handsets (C4040, C4020, C4010Ex, C4010) | 3 | N/A | User Guides considered sufficient | N/A
Products GA in 1999-Q2 2001 | Use '+' to UnGroup and '-' to Group
Products GA for 2001/2002
Meridian 1 Core
Rls 25.40 | 3 |  | PBT/CBT | 25648 Meridian 1 Rls 25.40 Features PBT
SIPE (with R25.40) | 3 |  | Virtual Classroom (5 Hours) | 25649 Meridian 1 Survivable IPE
Rls 26 |  |  | TBD
MIPCD | 3 |  | PBT | Meridian Integrated Personal Call Director, 25056, Self Paced - 8 Hours.
Miran III |  |  | NTPs sufficient for distributors upgrading from MIRAN II. Tech transfer slides will complement NTPs.
MICB III | 3 |  | Tech Transfer slides will be available on the delta between MICB II and MICB III. | MICB Course 25064 (PBT - MICB 1)
DDP2 - PRI2/DTI pack replacement | N/A |  | Product NTPS are sufficient
Terminals and Accessories
Ascom Smile2 | N/R |  | Same courses as Smile 1
Meridian Set M39xx Phase 3 |  |  | Interactive CBTs for end users, see details on http://www.nn-knowledgeservices-emea.com/ Under Meridian 1, M3901 to M3905 | Code 85181: M3901 Code 85182: M3902 Code 85183: M3903 Code 85184: M3904 Code 85185: M3905 Also Code 25646 Meridian 1 Upgrade Release 24 to 25 Features and 3900 sets Duration: 1 Day
IP Telephony on Meridian 1
IP Line and i2004 IP Set | 3 |  | Full training: Leader led course, "IP Telephony Gateway 2.0 (Trunk & LineSide/i2004)" Course Number: 25096A Channels trained on ITG Trunk 2.0: PBT "Meridian Internet Telephony Gateway (ITG) Line Side / i2004 set", Course 25297 | IP Telephony Gateway 2.0 (Trunk & LineSide/i2004) / Course Number: 25096A / Leader Led Training Meridian ITG Line Side /i2004 set / Course Number: 25297 / PBT
IP Line 2.2 and i2050 softphone | 3 |  | Same courses as IP Line and i2004 IP set - see above
IP Line 3.0 |  |  | TBD
ITG Trunk |  |  | Leader Lead: 25096 or 25096A (includes i2004) Full ITG 2.0 training, that end with one day on IP LC. This training also includes training on ITG 1.0. Prerequisites as per ITG 1.0 course. PBT (25296) to cover ITG 2.0 for people already trained on ITG 1.0 ; pre requisite for this one is to be already trained on ITG 1.0. | IP Telephony Gateway 2.0 training / 25096 / 3days IP Telephony Gateway 2.0 (Trunk & LineSide/i2004) / 25096A / 3 days
Remote Solutions
Remote Office 9150 (SW upissue 1.3.4) |  |  | CBT | Course number 85602
Remote Office 9110 (footstand) | 3 |  | PBT | Course number 85608
Remote Office 9115 (external) | 3 |  | PBT | Course number 85608
Wireless Solutions
MDECT_Messaging |  | 2002-05-01 | CD-ROM | DECT Messaging / 35873 / 1 Day
802.11 Wireless Gateway for Meridian 1 | 1
MDECT C4012 Handset | 3 | 2002-11-01 | User Guide | N/A
MDECT C4030 Handset | 3 | 2002-11-01 | User Guide | N/A
System Management
OTM | 3 |  | CBT / Leader Led | 0316T OTM Fundamentals (CBT, 4 hours); 0317C OTM Application & Web Services (4 Days); 0318C OTM Telecom Billing System (3 days); 0319C OTM Installation & Maintenance (1 day)
MDECT OTM Manager | 3 | July | PBT | 35139 OTM DECT - plus incorporating into leader lead courses 35870 and 35875
Succession CSE
Succession CSE Rls1.1 |  |  | Tech Training (Post-sales): 1. For partners that have introduced IP enabled Meridian: 2 day hands-on workshop, course 25519 (not mandatory, but highly recommended) OTM Training is compulsory 2. For partners that have not introduced IP enabled Meridian: At minimum need to take Tech training courses for ITG Trunk 2.0, I2004 Ether Set, and the Succession CSE Workshop is Mandatory OTM Training is compulsory Pre-sales Training: "Succession CSE 1000 Pre-sales Course", course S00605, 2 days Mandatory for all partners, intended for personnel in sales roles. Sales Training: "Selling Succession CSE 1000 Solutions" , course S00604, 1 day Mandatory for all partners, intended for personnel in sales and sales-related roles. For Sales and Pre-sales course bookings, see at the end of this spreadsheet | Post-sales Training: Course 25519 - Succession CSE 1000 Workshop - 2 days Pre-sales Training: Course S00605 - Succession CSE 1000 Pre-sales Course - 2 days Sales Training: Course S00604 - Selling Succession CSE 1000 Solutions - 1 day
Succession CSE 1000 Rls2.0 |  | 2002-09-01 | Sales and Pre-sales Training: same as for Succession CSE 1000 Rls1.1 Tech Training (Post-sales): workshop for engineers trained on Rls1.1 course 85615 SCSE 1000 rel 2.0 Workshop. | Post-sales Training: Course 85615 - Succession CSE 1000 Workshop - 2 days - for SCSE Rls1.1 experienced engineers Pre-sales Training: Course S00605 - Succession CSE 1000 Pre-sales Course - 2 days Sales Training: Course S00604 - Selling Succession CSE 1000 Solutions - 1 day
Messaging
Call Pilot 1.07 software |  |  | 1. First Introduction: 25820 CallPilot System Site Installation 25810 CallPilot Administration (Regular) 25830 CallPilot Networking 2. Upgrade from Call Pilot 1.06: TBA - Call Pilot Upgrade from 1.06 to 1.07 | 25820 CallPilot System Site Installation / LLT / 1 day 25810 CallPilot Administration (Regular) / LLT / 5 days 25830 CallPilot Networking / LLT / 2 days TBA - Call Pilot Upgrade from 1.06 to 1.07 / CBT -available on request from PLI
Call Pilot 2.0 Software |  | 2002-10-01 | Virtual Classroom | 25806 - CallPilot 1.07 to 2.0 Delta / 1 day
Call Pilot 201i server |  |  | NTP's | Not Applicable
Meridian Mail 13.14 upissue |  |  | Upgrade to Mail 13: 25529 MM 12 to 13 Upgrade Upgrade to Mail 12:- 25507 MM Networking to Rlse 12 25512 MM Rlse 9 to 10 Upgrade 25513 MM Rlse 10 to 11 Upgrade 25515 MM Rlse 10 to 11 Upgrade 25517 MM Rlse 11 to 12 Upgrade 25525 EC Mail Install to Rlse 13 25523 MM Administration (to Rlse 13) Meridian Mail Reporter | 25507 MM Networking to Rlse 12 / LLT/ 1 day 25512 MM Rlse 9 to 10 Upgrade / PBT 25513 MM Rlse 10 to 11 Upgrade / PBT 25515 MM Rlse 10 to 11 Upgrade / PBT + 1 day LLT 25517 MM Rlse 11 to 12 Upgrade /PBT 25529 MM Rlse 12 to 13 Upgrade /PBT 25525 EC Mail Install to Rlse 13 / LLT / 1 day 25523 MM Administration (to Rlse 13) / LLT / 5 days To go from MM9 - MM13, all PBT's would be required as new features were introduced with each Rlse 1 Day leader Led Course No 25541
CallPilot Mini Release 1.5 |  | 2002-09-01 | Virtual Classroom | 0016F - Callpilot Mini Installation and Administration Release 1.5 / 1 day
BCM
BCM 2.5 |  | Q2-2001 | See course details | 25034 - Business Communications Manager Installation - 2 Days - Leader Lead 25039 - Business Communications Manager 2.5 Delta - 4 Days - Leader Lead 25041 - Business Communications Manager 2.5 Installation and Maintenance - 5 Days - Leader Lead 25042 - Business Communications Manager 2.5 DECT I&M - 2 Days - Leader Lead 25043 - Business Communications Manager 2.5 Voice Messaging - 2 Days - Leader Lead 25044 - Business Communications Manager 2.5 Advanced Voice Programming - 2 Days - Leader Lead 25047 - Business Communications Manager 2.5 Data - 2 Days - Leader Lead 25048 - Business Communications Manager 2.5 CTI - 1 Day - Leader Lead 25049 - Business Communications Manager 2.5 Call Centre - 2 Days - Leader Lead 0178T - Business Communications Manager Training for Sales - 4 Hours - CBT on CD-ROM
BCM 3.0
Contact Centre Portfolio
SCCS Rls 1.1 incl. GRTD
SCCS Rls 1.5 | 3 |  | 1. First Introduction: 35401 SCCS 1.5 Overview 35411 SCCS Install & Conf of Ngen Server 35321 SCCS Client S/w Install & Config 35430 SCCS Agent/Supervisor Features 35440 SCCS Basic Client Administration 35450 SCCS Basic Cal Scripting Admin 35460 SCCS Advanced Call Scripting Admin 35471 SCCS Call Reporting Admin 35495 Introduction to Symposium Management | 35401 SCCS 1.5 Overview / LLT / 1 day 35411 SCCS Install & Config on Ngen Server / LLT / 4 days 35421 SCCS Client S/W Install & Config / LLT / 1 day 35430 SCCS Agent/Supervisor Features /LLT / 0.5 days 35440 SCCS Basic Client Admin /LLT / 2 days 35450 SCCS Basic Call Scripting Admin /LLT / 2 days 35460 SCCS Advanced Call Scripting Admin /LLT / 3 days 35471 SCCS Call Reporting Admin /LLT / 2 days 35495 Introduction to Symposium Management /LLT/2 days
SCCS Rls 3.0 Nodal | 3 |  | as above, SCCS 3.0 now included | 35570 SCCS Nodal Upgrade
SCCS Rls 3.0 Networking | 3 |  |  | 35571 SCCS Network Admin
SCCS Rls 4.0 | 3 |  |  | 35573 SCCS 3.0 to 4.0 Nodal update 3 days 35413 Symposium Rel 4.0 Installation and Configuration of Server & Client (PVI Platform) 4 days
Symposium Config. Tool | N/A |  | No Training required.
SCCS 4.0 Web Client |  |  | Leader led and PBT | 35614 Symposium Web Client 4.0 Installation and Configuration of Client PC and Server 1 day 31615 Symposium Web Client 4.0 Basic Client Administration 2days
Symposium Express CC | 3
Symposium Express CC 2.0 | 3 |  |  | 35551 SECC 1.0 & 2.0 Install & Com / PBT 35552 SECC 1.0 & 2.0 Install & Comm - New for Rlse 2.0 Addendum to PBT / PBT 35556 SECC 1.0 & 2.0 Install & Comm / LLT / 2 days 35561 SECC Call Centre Administration /LLT / 1 day
Symposium Express CC 3.0 | 3 |  | Leader led and PBT | 35564 SECC Rel. 2 to 3 D-Training/1day 35563 SECC VPS Card/1day 35557 SECC Rel. 3 Installation/1day 35562 SECC Rel. 3 Administration/1 day 35565 SECC Rel. 2 to 3 D - PBT
SWRS Rls 1.0
SWCP 3.0 |  |  | Leader led | 35574 SWCP Overview & Administration 2 days 35575 Installation & Configuration 3 days
Symposium Agent Rls 1 |  | N/A |  | N/A
Symposium Agent Rls 1.1 | 3 |  | 1. First Introduction: 35610 Symposium Agent End User 35620 Symposium Agent Client / TAPI Server Install & Basic Configuration 35630 Symp Agent (intermediate Plus) Install & Administrator | 35620 Symp Agent Client /TAPI Server Install & Basic Config /LLT /1.5 Days 35630 Symp Agent (Intermediate Plus) Install & Administrator /LLT /1.5 Days 35610 Symp Agent End User / LLT/ 1 day
Symposium Agent Rls 2.0
Agent Greeting 2.0 |  |  | PBT | 35613 - Agent Greeting 2.0 PBT
MAX 9 | 3 |  | 1. First Introduction:- 35022 MAX install & Mtce to Rlse 6,7,8, 9 35065 MAX 7 to 8 & 9 Upgrade 2. Upgrade to Max 9 Current courses amended | ,9 / LLT / 5 days 35065 MAX 7 to 8,9 Upgrade / LLT / 2 days
MAX 10 | 3 |  | 1. Max 9 to MAX10 delta training course available on request. Please contact Channel Readiness Manager for info.
MTE 9 | N/A |  | 1. First Introduction:- 35022 MAX install & Mtce to Rlse 6,7,8, 9 35065 MAX 7 to 8 & 9 Upgrade 2. Upgrade to Max 9 Current courses amended | ,9 / LLT / 5 days 35065 MAX 7 to 8,9 Upgrade / LLT / 2 days
Link-CCR CoRes Rls 6.42 | 3 |  | 1. First Introduction:- 35205 CCR Install & Mtce (IPE & AEM) Rlse 3 35230 CCR Feature Admin Rlse 3 35245 Meridian Link Install & Mtce (IPE & AEM) Rlse 5 35261 Meridian Link Install & Mtce Rlse 4 to 5 | 35205 CCR Install & Mtce (IPE & AEM) Rlse 3 / LLT / 1.5 days 35230 CCR Feature Admin Rlse 3 / LLT / 3 days 35245 Meridian Link Install & Mtce (IPE & AEM) Rlse 5 / LLT / 1.5 days 35261 Meridian Link Install & Mtce Rlse 4 to 5 / PBT
Symposium Link 6.01
TAPI SP for M1, Rls 2.1 | 3 |  | 1. First Introduction: 35620 Symposium Agent Client / TAPI Server Install & Basic Configuration | 35620 Symp Agent Client /TAPI Server Install & Basic Config /LLT /1.5 Days
TAPI SP for M1, Rls 2.2 | 3 |  | 1. First Introduction: 35621 Symposium Agent Client / TAPI Server Install & Basic Configuration | 35621 Symp Agent Client /TAPI Server Install & Basic Config /LLT /1.5 Days
Call Manager PRO |  |  | 1. First Introduction: 35941 Call Manager | 35941 Call Manager /LLT / 1 day
Desktop TAPI SP2.0 (for MCAs) | N/R
Meridian Max 7.52 ( Y2K Upissue)
Meridian NAC 2.5x (Y2K Upissue) |  |  | 1. First Introduction:- 35110 NAC2 - Install & Mtce | 35110 NAC2 - Install & Mtce / LLT / 1.5 days
Call Recorder (Comverse)
Multimedia Web API |  |  | Training will be delivered by Package Services through workshops
| N/R | training not required
overdue
under development
available
Maid. courses: Phone:+44.990.502.501 Fax: +44.1628.438.894
Munich courses: Phone: +49.89.3505.2375 Fax: +49.89.3505.2363 email: training@nortel-dasa.de
PBT Courses: Karen Ballinger +44 162-843-8597 email : kballi@nortelnetworks.com
Succession CSE 1000 Sales and pre-sales course details and bookings can be obtained from Cindy Warren, Tel: 44 (0)1628 438248 Fax: 44 (0) 1628 437547 e-mail: cindywar@nortelnetworks.com
URL for the training web site is http://www.nortelnetworks.com/training
Assistance can be obtained from the Call Centre which is on Euro Freephone 00800 8008 9009 or International +44 (0)208 920 4618
Orders for Paper Based Training and Technology Based Training (PBT & TBT) under US$5,000
can now be made by Credit Card payment at the following URL.
Internet site : http://www.nortelnetworks.com/training
Note on A119: Multimedia Web API: Thin-client API and Applications for Telephony (CTI) and Multimedia Communications Release Content Agent/Employee facing API and Applications Thin-client Telephony Toolbar & Screen Pops Auto-dialing Web Directories with LDAP Customer facing API and Application Click-to-Talk Open Architecture initially focused on M1 / CSE 1K Ease of new service implementation & customisation of services Ability to access services through a variety of user interfaces (esp. the Web) according to the user’s interface of choice. Delivery of first-phase applications - Web Dial, Click To Talk, Web Phone
Training
Products
Courses are available to order at: http://www.nortelnetworks.com/training Click on EMEA and language. On the home page select 'Catalog Search' and then enter course number or select Product Group e.g. 'Succession Softswitch Portfolio'. Nortel Networks Knowledge Services Phone number + 44 20 8920 4618 or European Freephone 00800 8008 9009

## Documentation
Please follow these procedures for obtaining Meridian 1/Succession CSE 1000 Customer Documentation:
Online Documentation:
There is no charge for online documentation.
Internal and External Customers:
Access Nortel Networks web page: www.nortelnetworks.com
Click on Technical Documentation
Scroll through document listing until you see the document you need